## Start Here
Cohort Logic — Security & Compliance Tracker
SCOPE (2026-07-21): Launching Class Builder + Schedule Builder only (browser-only, no student data stored). CICO + Referral Tracking = Phase 2. Each item is tagged Phase 1 / Phase 2. See compliance/16_Go_To_Market_Scope.md.
Purpose
A single living plan to get Cohort Logic production-ready to sell to schools nationwide — covering FERPA & student-data privacy, security hardening, business/legal/insurance, the questionnaire districts will send you, and the product gaps in between.
How the tabs work
• Dashboard — live rollup: how many items per workstream are done / in progress / not started, and how many P0 (must-have) items remain.
• FERPA & Privacy, Security & Infra, Business & Insurance, Product & Go-Live — the working checklists. Each row has an ID, priority, status, owner, and next action.
• School Vendor Q&A — the recurring questions procurement/IT send, each with a prepared answer, the evidence, and a readiness rating (Ready / Partial / Gap).
How we'll manage it
This is the tracker I (Claude) maintain for you. Tell me things like “mark SE-07 done,” “what are my open P0 items?,” “add a task for X,” or “what do I still owe a district that just sent a questionnaire?” — and I'll update the file and re-share. IDs (FE-/SE-/VQ-/BI-/PR-) are stable handles for that.
Status values (dropdowns)
Checklists: Not started · In progress · Blocked · Done · N/A Vendor Q&A: Ready · Partial · Gap
Priority: P0 = must-have before selling · P1 = needed early · P2 = important, can follow
The fastest path to a sellable posture (suggested first moves)
1. Upgrade Supabase to Pro + verify backups (SE-07/08). 2. Sign the Supabase & Cloudflare DPAs and publish a sub-processor list (FE-05). 3. Bind cyber + E&O insurance (BI-04/05). 4. Get a lawyer-reviewed DPA/NDPA template and finalize ToS (FE-02/03, BI-08). 5. Write the data map, retention policy and incident-response/breach plan (FE-04/07/12, SE-12).
Important disclaimer
This tracker is an organizational tool, not legal, insurance, or financial advice. FERPA/state-law, contract, and insurance items must be reviewed by a licensed attorney and a licensed insurance broker before you rely on them. Rows marked “Attorney” or “Broker” as owner are flagged precisely because they need a professional.
Last updated by Claude: 2026-07-21

## Dashboard
Cohort Logic — Production Readiness Dashboard
Live rollup of the workstream tabs. Counts update automatically as Status cells change.
Workstream | P0 items | Not started | In progress | Blocked | Done | % Done
FERPA & Privacy
Security & Infra
Business & Insurance
Product & Go-Live
TOTAL
School Vendor Questionnaire Readiness
Ready |  | Partial |  | Gap
Priority key: | P0 = must-have before selling ¦ P1 = needed early ¦ P2 = important, can follow
Phase 1 launch focus — Class Builder + Schedule Builder (no student data stored)
Phase 1 items | Done | In progress | Not started | % Phase 1 done
Phase 2 (CICO / Referral Tracking) is deferred until product-market fit — see the Go-To-Market Scope memo (compliance/16).

## FERPA & Privacy
FERPA & Student Data Privacy
Legal basis, contracts, data governance. Attorney review required where noted — this tracker is not legal advice.
ID | Area | Task | Why it matters | Priority | Status | Owner | Depends on | Next action / notes | Phase
FE-01 | Legal basis | Document the FERPA “school official” exception posture (34 CFR §99.31(a)(1)): legitimate educational interest, direct control by the school, use limited to the authorized purpose, no redisclosure. | The legal basis that lets you process student PII without separate parental consent. Every district relies on it. | P0 | In progress | Michael + Attorney |  | Draft memo at compliance/03_FERPA_School_Official_Posture.md — needs attorney review. | Phase 1
FE-02 | Contracts | Create a signable Data Processing Agreement (DPA) template for schools/districts. | Districts will not sign without one; it is the core of every procurement package. | P0 | In progress | Michael + Attorney | FE-01 | DPA/NDPA readiness at compliance/07_DPA_and_NDPA_Readiness.md — attorney to produce own-paper DPA/MSA. | Phase 1
FE-03 | Standards | Adopt the SDPC National Data Privacy Agreement (NDPA) and join the Student Data Privacy Consortium. | The de-facto national standard; many districts require the NDPA exhibit specifically. | P0 | In progress | Michael | FE-02 | NDPA v2.2 plan in compliance/07_... — join SDPC, prep Exhibit A/B/F, sign Exhibit E (piggyback). | Phase 1
FE-04 | Data map | Produce a data inventory / data-flow map: every PII element collected, its purpose, storage location, access roles, and retention. | Required by NY Ed Law 2-d, IL SOPPA and nearly every vendor questionnaire. | P0 | In progress | Claude |  | Data map drafted at compliance/01_Data_Inventory_and_Data_Map.md — confirm audit_log PII + Supabase US region. | Phase 1
FE-05 | Sub-processors | Publish the sub-processor list (Supabase / AWS US region, Cloudflare) and obtain each sub-processor DPA. | Districts require the full chain of custody. The Supabase DPA is already an open item in the security audit. | P0 | Not started | Michael |  | Sign Supabase DPA; get Cloudflare DPA; publish list on the trust page. | Phase 1
FE-06 | Data residency | Confirm and document that all student data (DB + backups) is stored in a US region. | Several states/districts require US-only storage. | P0 | Not started | Michael |  | Verify Supabase project region in the dashboard; capture attestation. | Phase 1
FE-07 | Retention | Write a data retention & deletion policy; verify per-school deletion on offboarding (admin “Wipe Data” exists) covers all child tables + backups; document the parent/student deletion path via the school. | FERPA + state laws require a defined retention schedule and deletion on request/termination. | P0 | In progress | Michael + Claude | FE-04 | Policy drafted at compliance/02_Data_Retention_and_Deletion_Policy.md — set [DECIDE] windows; verify wipe covers referrals + audit_log. | Phase 1
FE-08 | Privacy policy | Attorney review of privacy.html for FERPA / COPPA / SOPIPA / NY 2-d alignment; add an explicit “no sale, no targeted advertising, no secondary use” statement. | Table-stakes for schools; the current policy has not had legal review. | P0 | In progress | Attorney |  | Production draft at compliance/08_Privacy_Policy_DRAFT.md — attorney review, then port to privacy.html (fixes Netlify/Schedule/Referrals/demographics gaps). | Phase 1
FE-09 | COPPA | Document the COPPA posture for under-13 students (school acts as agent for parental consent for educational use). | Behavior / CICO data on young students draws COPPA scrutiny. | P1 | Not started | Michael + Attorney |  | Reflect in privacy policy + DPA. | Phase 2
FE-10 | State laws | Compile a state student-privacy compliance matrix (start: CA SOPIPA, NY Ed Law 2-d, IL SOPPA, CO, VA, TX). | Selling nationwide means multi-state obligations; NY 2-d and IL SOPPA are notably strict. | P1 | In progress | Michael + Claude |  | State matrix at compliance/06_State_Student_Privacy_Matrix.md — confirm [VERIFY] statute cites/timelines with counsel. | Phase 2
FE-11 | NY Ed Law 2-d | If targeting NY: prepare a Parents Bill of Rights and a Data Security & Privacy Plan aligned to NIST CSF. | NY districts legally cannot sign without these. | P2 | Not started | Michael | FE-10 | Only if pursuing the NY market. | Phase 2
FE-12 | Breach | Document a data-breach notification process with state-law timelines and template notices. | Required by contracts and many state laws (some require notice in ≤ 7 days). | P0 | In progress | Michael + Claude |  | Breach policy at compliance/05_Data_Breach_Notification_Policy.md — 72h default / 7-day hard ceiling. | Phase 2
FE-13 | Access rights | Document the process for parent/student data access & correction requests, routed through the school. | FERPA access and amendment rights. | P1 | In progress | Michael | FE-07 | Runbook drafted at compliance/14_Data_Request_Runbook.md — set turnaround + privacy@ intake. | Phase 2
FE-14 | Training | Adopt an annual data-privacy & security training / acknowledgement (even solo now; scales with hires). | Questionnaires routinely ask about staff privacy training. | P2 | Not started | Michael |  | Document the policy now so there is something to point to. | Phase 1

## Security & Infra
Security & Infrastructure Hardening
Technical controls for a production, multi-tenant SaaS. Items marked Done are verified by the daily security agent.
ID | Area | Task | Why it matters | Priority | Status | Owner | Depends on | Next action / notes | Phase
SE-01 | Access control | Multi-tenant data isolation via Postgres RLS (school_id) + role-based access (user / school_admin / super_admin). | Prevents cross-school data leakage; the single most important control. | P0 | Done | — |  | Verified daily by the security-compliance agent. | Phase 1
SE-02 | Audit | FERPA audit log of data access and changes (audit_log). | Required for FERPA and for incident forensics. | P1 | Done | — |  | In place. | Phase 1
SE-03 | Transport | TLS + security headers (CSP without unsafe-inline, X-Frame-Options, nosniff, Referrer-Policy, Permissions-Policy) via Cloudflare. | Encryption in transit; a standard questionnaire item. | P0 | Done | — |  | Verified live by the security agent. | Phase 1
SE-04 | Authentication | Email verification, 15-minute session timeout, admin MFA available. | Baseline account security. | P0 | In progress | Michael | SE-05 | MFA is available but enrollment is not yet mandatory — see SE-05. | Phase 1
SE-05 | Authentication | Enforce mandatory MFA for all admin/staff accounts (block until a factor is verified). | Open audit finding; districts increasingly require enforced MFA. | P1 | Not started | Michael + Claude |  | Flip admin-mfa.js from soft reminder to hard enforcement. | Phase 1
SE-06 | Monitoring | Automated daily security & compliance audit agent + admin Security dashboard. | Continuous control monitoring; good evidence for buyers. | P1 | Done | — |  | This agent. | Phase 1
SE-07 | Resilience | Upgrade Supabase to Pro (stops the project pausing on inactivity; unlocks PITR backups). | Required before onboarding any paying school. | P0 | Not started | Michael |  | Already flagged in CLAUDE.md pending list. | Phase 1
SE-08 | Backups | Enable and document automated backups + Point-in-Time Recovery; run a test restore and record RPO/RTO. | Data durability; a DR and questionnaire requirement. | P0 | Not started | Michael | SE-07 | Document the restore runbook. | Phase 1
SE-09 | Encryption | Confirm and document encryption at rest (Supabase/Postgres + backups); obtain the provider attestation. | Common questionnaire item; pairs with SE-03. | P0 | Not started | Michael |  | Capture Supabase/AWS attestation language. | Phase 1
SE-10 | Assessment | Commission a third-party penetration test / security assessment; set an annual cadence. | Larger districts ask for pen-test evidence. | P1 | Not started | Michael |  | Get quotes; schedule the first test. | Phase 2
SE-11 | Vuln mgmt | Establish dependency/vulnerability scanning (npm audit, Dependabot) as an ongoing process. | Ongoing security hygiene. | P2 | Not started | Claude |  | Add to CI / the pre-deploy gate. | Phase 1
SE-12 | Incident response | Write an Incident Response Plan (roles, severity levels, comms, timelines). | Required by contracts and by FE-12. | P0 | In progress | Michael + Claude |  | IR plan drafted at compliance/04_Incident_Response_Plan.md — fill [FILL] counsel/insurer/provider contacts. | Phase 1
SE-13 | BC/DR | Write a Business Continuity / Disaster Recovery plan. | Questionnaire item; ties directly to backups. | P1 | In progress | Michael | SE-08 | BC/DR plan drafted at compliance/12_Business_Continuity_and_DR_Plan.md — set RPO/RTO; depends on Supabase Pro (SE-07). | Phase 1
SE-14 | Uptime | Add uptime monitoring + alerting + a public status page. | SLA credibility and a questionnaire item. | P1 | Not started | Michael |  | e.g. UptimeRobot / BetterStack + a hosted status page. | Phase 1
SE-15 | Passwords | Enable Supabase breached-password protection + a strong password policy. | Cheap, high-value control. | P2 | Not started | Michael |  | Supabase Auth settings toggle. | Phase 1
SE-16 | Secrets | Document secrets management (service-role key handling + the rotation manifest). | Partly done via security/rotation-manifest.json. | P2 | In progress | Michael |  | Secrets policy drafted at compliance/13_Secrets_Management.md. | Phase 1
SE-17 | SOC 2 | Decide on a SOC 2 Type I/II roadmap (build now vs defer). | A major enterprise-district sales enabler, but costly and time-consuming. | P2 | Not started | Michael |  | Decision item; consider Vanta/Drata when revenue supports it. | Phase 2
SE-18 | Edge | Review Cloudflare WAF + rate limiting on auth endpoints. | Brute-force and abuse protection. | P2 | Not started | Michael |  | Configure WAF rules. | Phase 1

## School Vendor Q&A
School / District Vendor Questionnaire Readiness
The recurring questions procurement and district IT send. Goal: a prepared answer + evidence for every row before the first questionnaire arrives.
ID | Theme | Typical district question | Our current answer | Evidence / where | Status | Action to be answer-ready | Phase
VQ-01 | Company | Legal name, entity type, EIN, years in business, primary contact. | Cohort Logic (confirm exact LLC name + EIN). | Business & Insurance tab | Partial | Confirm entity/EIN (footer 'PBC' vs LLC discrepancy) + document in one place. | Phase 1
VQ-02 | Data collected | What student PII do you collect and why? | Name, grade, homeroom, behavior/CICO records, referral data, limited demographics for equity reporting. No rosters stored for Class Builder. | Data map (FE-04) | Partial | Data map drafted (01_...); finalize + confirm flags. | Phase 1
VQ-03 | Hosting | Where is data hosted? Cloud provider and region? | Supabase (managed Postgres on AWS) + Cloudflare. Confirm US region. | FE-06 | Partial | Confirm + document region. | Phase 1
VQ-04 | Encryption | Is data encrypted in transit and at rest? | In transit: yes (TLS + headers). At rest: pending attestation. | SE-03 done / SE-09 pending | Partial | Obtain at-rest attestation. | Phase 1
VQ-05 | Access control | How is tenant data isolated? RBAC? MFA? | Postgres RLS per school_id; 3-tier roles; admin MFA available. | SE-01 / SE-04 | Ready | Note that mandatory MFA is in progress (SE-05). | Phase 1
VQ-06 | Sub-processors | List your sub-processors and their agreements. | Supabase, Cloudflare. DPAs not yet signed. | FE-05 | Gap | Sub-processor list drafted (01_...); sign Supabase + Cloudflare DPAs to close. | Phase 1
VQ-07 | Retention / deletion | What is your retention schedule and deletion-on-termination process? | Admin Wipe Data exists; formal policy pending. | FE-07 | Partial | Retention/deletion policy drafted (02_...); set windows + verify wipe scope. | Phase 1
VQ-08 | Breach notification | What is your breach notification process and timeline? | Not yet documented. | FE-12 / SE-12 | Partial | Breach policy (05_...) + IR plan (04_...) drafted; fill contacts to reach Ready. | Phase 2
VQ-09 | Compliance | Are you FERPA / COPPA / state-law compliant? Provide statements. | Architecture aligns; statements not attorney-reviewed. | FERPA tab | Partial | FERPA posture (03_...) + state matrix (06_...) drafted; needs counsel-reviewed statements. | Phase 1
VQ-10 | DPA / NDPA | Will you sign our DPA / the SDPC NDPA? | Yes in principle; no template ready yet. | FE-02 / FE-03 | Partial | NDPA readiness brief (07_...) drafted; join SDPC + have signable template to reach Ready. | Phase 1
VQ-11 | Insurance | Do you carry cyber liability and E&O insurance? Limits? COI? | Not yet bound. | Business tab | Partial | Michael obtaining cyber + E&O coverage; keep COI ready once bound (BI-04/05/07). | Phase 1
VQ-12 | Audits | Do you have SOC 2 or a recent penetration test? | No SOC 2; no pen test yet. | SE-10 / SE-17 | Gap | Pen test first; SOC 2 as a later roadmap item. | Phase 2
VQ-13 | Accessibility | Are you WCAG 2.1 AA compliant? Provide a VPAT. | No VPAT yet. | Product tab (PR-05) | Gap | Commission an accessibility audit + VPAT. | Phase 1
VQ-14 | SSO / rostering | Do you support Google / Clever / ClassLink SSO and roster sync? | Email/password only today. | Product tab (PR-06) | Gap | Roadmap SSO/rostering — a major K-12 adoption factor. | Phase 2
VQ-15 | Support / SLA | What is your uptime SLA, support channel and response time? | Not formally defined. | Product tab (PR-03/07) | Partial | Define SLA + support commitments. | Phase 1
VQ-16 | Personnel | Background checks / security training for staff with data access? | Solo founder today; no formal program. | FE-14 | Partial | Document the policy (scales with hiring). | Phase 1
VQ-17 | Data use | Do you sell data or use it for advertising / secondary purposes? | No — never. Make it explicit in policy + contract. | FE-08 | Partial | Explicit no-sale/no-ads/no-secondary-use in privacy draft (08_...); finalize + attorney review. | Phase 1
VQ-18 | References | Can you provide customer references or pilot results? | None documented yet. | — | Gap | Gather references/testimonials from pilots. | Phase 1

## Business & Insurance
Business, Legal & Insurance
Entity, contracts and coverage. Insurance rows are informational only — consult a licensed broker; this is not insurance or financial advice.
ID | Area | Task | Why it matters | Priority | Status | Owner | Depends on | Next action / notes | Phase
BI-01 | Entity | Confirm LLC formation, registered agent, and a current operating agreement. | Contracts require a valid, in-good-standing legal entity. | P0 | Not started | Michael |  | Confirm exact legal entity — security.html footer says 'PBC', other materials imply LLC; make consistent. | Phase 1
BI-02 | Tax | Have EIN + a signed W-9 ready to hand to districts. | Districts require a W-9 to set you up as a vendor/payee. | P0 | Not started | Michael | BI-01 | Keep a signed W-9 on file. | Phase 1
BI-03 | Banking | Business bank account + clean accounting separation. | Basic operations + audit readiness. | P1 | In progress | Michael |  | Confirm (bookkeeping already underway). | Phase 1
BI-04 | Insurance | Obtain Cyber Liability / data-breach insurance (districts often require $1-2M). | Frequently a contractual requirement and protects the business after an incident. | P0 | In progress | Michael + Broker |  | Michael obtaining cyber liability coverage (broker). | Phase 1
BI-05 | Insurance | Obtain Technology E&O / Professional Liability. | Covers claims that your software caused a customer loss. | P0 | In progress | Michael + Broker |  | Michael obtaining technology E&O coverage (broker). | Phase 1
BI-06 | Insurance | General Liability (commonly a BOP bundle). | A common contract requirement. | P1 | In progress | Michael + Broker |  | Michael obtaining general liability / BOP (broker). | Phase 1
BI-07 | Insurance | Keep a Certificate of Insurance (COI) ready for procurement. | Districts request a COI before signing. | P1 | Not started | Michael | BI-04 | Store a current COI to attach to questionnaires. | Phase 1
BI-08 | Legal | Attorney-reviewed Terms of Service (currently terms-beta.html). | “Beta” terms are not adequate for paid district contracts. | P0 | In progress | Attorney |  | Production ToS draft at compliance/09_Terms_of_Service_DRAFT.md — replaces beta agreement; attorney review then port to terms.html. | Phase 1
BI-09 | Legal | Master Services / Subscription Agreement for schools. | The commercial contract for paying customers. | P0 | In progress | Attorney |  | MSA skeleton at compliance/10_Master_Services_Agreement_SKELETON.md — attorney to draft; contract doc, not a web page. | Phase 1
BI-10 | Legal | DPA template as a contract exhibit (mirrors FE-02). | The data-handling terms of the MSA. | P0 | Not started | Attorney | FE-02 | Keep the legal and product copies in sync. | Phase 1
BI-11 | Legal | Acceptable Use Policy. | Governs how customers may use the product. | P2 | In progress | Michael |  | AUP draft at compliance/11_Acceptable_Use_Policy_DRAFT.md. | Phase 1
BI-12 | IP | Consider a trademark for “Cohort Logic”. | Brand protection as you scale nationally. | P2 | Not started | Michael |  | Optional; search availability first. | Phase 2
BI-13 | Procurement | Prepare to register in district/state vendor systems as required. | Some districts require formal vendor registration. | P2 | Not started | Michael |  | Handle as encountered. | Phase 2
BI-14 | Counsel | Identify ed-tech/privacy legal counsel + breach counsel. | Speed matters for both contract review and incident response. | P1 | Not started | Michael |  | Have someone on call before the first deal. | Phase 1

## Product & Go-Live
Product & Go-Live Readiness
The commercial and product gaps between “works” and “sellable nationwide.”
ID | Area | Task | Why it matters | Priority | Status | Owner | Depends on | Next action / notes | Phase
PR-01 | Billing | Integrate a payment processor (Stripe) for subscriptions; wire to the subscriptions table. | You cannot sell without billing, and there is no processor yet. | P0 | Not started | Michael + Claude |  | Design plans + checkout + webhooks. | Phase 1
PR-02 | Onboarding | Build/document the school onboarding flow (provision school, first admin, roster import). | A smooth setup drives conversion and reduces support. | P1 | In progress | Michael + Claude |  | Admin tooling exists; formalize the flow. | Phase 1
PR-03 | Support | Define support channels + SLA + response-time targets. | A questionnaire item and a trust signal. | P1 | Not started | Michael |  | e.g. email + help desk; publish response targets. | Phase 1
PR-04 | Docs | Help center / user documentation. | Reduces support load; a procurement plus. | P2 | Not started | Michael |  | Start with top workflows per product. | Phase 1
PR-05 | Accessibility | Commission a WCAG 2.1 AA audit and produce a VPAT. | Increasingly required in K-12 procurement (Section 508 / ADA). | P1 | Not started | Michael |  | Feeds VQ-13. | Phase 1
PR-06 | SSO / rostering | Roadmap Google / Clever / ClassLink SSO + roster sync. | A major K-12 adoption and IT-approval factor. | P1 | Not started | Michael + Claude |  | Feeds VQ-14; sequence after billing. | Phase 2
PR-07 | Reliability | Publish an uptime SLA commitment + status page. | Ties to SE-14; buyers ask for it. | P2 | Not started | Michael | SE-14 |  | Phase 1
PR-08 | Infra cleanup | Delete the legacy Netlify site; confirm a single production path. | Reduces attack surface and deployment confusion. | P2 | Not started | Michael |  | Already in CLAUDE.md pending. | Phase 1
PR-09 | Pricing | Finalize pricing and plan tiers (pricing.html exists). | Needed for billing and sales conversations. | P1 | In progress | Michael |  | Confirm tiers before wiring Stripe. | Phase 1
PR-10 | Trust page | Expand security.html into a public Trust/Security page (controls, sub-processors, compliance posture). | A sales asset that pre-answers most questionnaires. | P1 | In progress | Michael + Claude | FE-05 | Trust page content drafted at compliance/15_Trust_Page_Content.md — product-aware reframe; port to security.html in website batch. | Phase 1